## Live records
Incremental cancellation cost calculation
ArtBuild workbook, version 2026.1. Amber inputs are editable; formulas are protected against accidental edits. General information, not legal advice.
Include incremental exit costs only. Completed work, material and trade totals belong in separate schedules.
Recorded net CAD |  |  | Includes all statuses |  |  | Review before inclusion
Item ID | Scope / item / unit | Counterparty / location | Signed quantity | Unit cost CAD | Gross cost CAD | Credit CAD | Net record CAD | Cost status | Evidence / basis | Review flag
Gross quantity times unit cost less confirmed recovery or release gives net exposure. This does not establish recoverability.
Record PO or trade reference, order date, delivery or cancellation action, ownership, due date and responsible person in Evidence / basis.
Keep estimates and disputed amounts visible. Transfer only reviewed lines to the final account; do not add this total to duplicated source costs.
All examples are fictional. Amounts use one consistent tax basis stated in evidence; no tax rate or legal charge is assumed.
Project / snapshot |  |  |  |  | Prepared / reviewed by

## Fictional examples
Incremental cancellation cost calculation
ArtBuild workbook, version 2026.1. Amber inputs are editable; formulas are protected against accidental edits. General information, not legal advice.
Include incremental exit costs only. Completed work, material and trade totals belong in separate schedules.
Recorded net CAD |  |  | Includes all statuses |  |  | Review before inclusion
Item ID | Scope / item / unit | Counterparty / location | Signed quantity | Unit cost CAD | Gross cost CAD | Credit CAD | Net record CAD | Cost status | Evidence / basis | Review flag
EX-01 | Secure site / crew hour | Fictional site crew | 4 | 100 |  | 0 |  | Actual | C01: incremental exit work only
EX-02 | Transport / truck trip | Fictional Harbour Haul | 3 | 200 |  | 100 |  | Estimate | C02: estimate with CAD100 credit
EX-03 | Cancelled storage / week | Fictional store | 0 | 50 |  | 0 |  | Actual | C03: zero charge confirmed
EX-04 | Remove signage / crew hour | Fictional site crew |  | 80 |  | 0 |  | Actual | C04: hours awaiting ticket
EX-05 | Exit cost correction / hour | Fictional site crew | -1 | 100 |  | 0 |  | Actual | C05: reverse one prior billed hour
Gross quantity times unit cost less confirmed recovery or release gives net exposure. This does not establish recoverability.
Record PO or trade reference, order date, delivery or cancellation action, ownership, due date and responsible person in Evidence / basis.
Keep estimates and disputed amounts visible. Transfer only reviewed lines to the final account; do not add this total to duplicated source costs.
All examples are fictional. Amounts use one consistent tax basis stated in evidence; no tax rate or legal charge is assumed.
Project / snapshot |  |  |  |  | Prepared / reviewed by