## Live records
Completed work assessment
ArtBuild workbook, version 2026.1. Amber inputs are editable; formulas are protected against accidental edits. General information, not legal advice.
Measure completed quantities at the cancellation snapshot. Valuation and actual cost are different measures.
Work value CAD |  |  | Includes all statuses |  |  | Review before inclusion
Item ID | Scope / item / unit | Counterparty / location | Measured quantity | Value rate CAD | Work value CAD | Actual cost CAD | Net record CAD | Review status | Evidence / basis | Review flag
Actual cost is recorded separately and is never added to measured value. Use signed correction quantities with the original item reference.
Record measurement date, scope, unit, photos and reviewed rate in Evidence / basis. Do not value both a composite item and its constituent materials.
Use one stable ID per item. Enter zero explicitly. Missing quantities or evidence block the total; duplicate IDs are flagged.
All examples are fictional. Amounts use one consistent tax basis stated in evidence; no tax rate or legal charge is assumed.
Project / snapshot |  |  |  |  | Prepared / reviewed by

## Fictional examples
Completed work assessment
ArtBuild workbook, version 2026.1. Amber inputs are editable; formulas are protected against accidental edits. General information, not legal advice.
Measure completed quantities at the cancellation snapshot. Valuation and actual cost are different measures.
Work value CAD |  |  | Includes all statuses |  |  | Review before inclusion
Item ID | Scope / item / unit | Counterparty / location | Measured quantity | Value rate CAD | Work value CAD | Actual cost CAD | Net record CAD | Review status | Evidence / basis | Review flag
EX-01 | Installed baseboard / m | Room A / site measure | 4 | 100 |  | 0 |  | Measured | Fictional M01: rate includes labour/material
EX-02 | Installed blocking / m | Room B / revised measure | 3 | 200 |  | 100 |  | Agreed measurement | Fictional M02: revised from four metres
EX-03 | Unstarted trim / m | Room C | 0 | 50 |  | 0 |  | Measured | Fictional M03: zero installed
EX-04 | Drywall patch / m2 | Room D / measure pending |  | 80 |  | 0 |  | Measured | Fictional M04: quantity unresolved
EX-05 | Measurement correction / m | Room A | -1 | 100 |  | 0 |  | Measured | Fictional M05: correct prior overmeasure
Actual cost is recorded separately and is never added to measured value. Use signed correction quantities with the original item reference.
Record measurement date, scope, unit, photos and reviewed rate in Evidence / basis. Do not value both a composite item and its constituent materials.
Use one stable ID per item. Enter zero explicitly. Missing quantities or evidence block the total; duplicate IDs are flagged.
All examples are fictional. Amounts use one consistent tax basis stated in evidence; no tax rate or legal charge is assumed.
Project / snapshot |  |  |  |  | Prepared / reviewed by