## Repairs
Deficiency investigation and repair tracker
ArtBuild workbook, version 2026.1. Amber inputs are editable; formulas are protected against accidental edits. General information, not legal advice.
An allegation is not a verified defect or an allocation of cost. Targets are internal planning dates.
As-of date | 2026-10-23
Total CAD
Item ID | Location / allegation | Finding status | Owner | Target date | Work status | Estimated CAD | Actual CAD | Variance CAD | Days to target | Review flag | Evidence / closure
Use one stable ID per issue. Put the actual observation, requirement, inspector and any limitation in the linked evidence record.
Completed means work performed. Verified closed additionally requires an inspection or review record in Evidence / closure.
Variance is actual less estimate; positive means over estimate. Enter zero explicitly; missing costs withhold the total.
Example rows are fictional and excluded from the Repairs sheet. Extend the 20-row range only after updating formulas and validation.
Project / contract |  |  |  |  | Prepared by / date

## Fictional examples
Deficiency investigation and repair tracker
ArtBuild workbook, version 2026.1. Amber inputs are editable; formulas are protected against accidental edits. General information, not legal advice.
An allegation is not a verified defect or an allocation of cost. Targets are internal planning dates.
As-of date | 2026-10-23
Total CAD
Item ID | Location / allegation | Finding status | Owner | Target date | Work status | Estimated CAD | Actual CAD | Variance CAD | Days to target | Review flag | Evidence / closure
D-01 | Window leak reported | Alleged | Sam | 2026-10-25 | Investigating | 500 | 0
D-02 | Trim joint measured | Verified finding | Jo | 2026-10-22 | In progress | 200 | 250
D-03 | Sealant repair tested | Verified finding | Jo | 2026-10-21 | Verified closed | 0 | 0 |  |  |  | Inspection R-03 by reviewer 2026-10-22
D-04 | Unpriced investigation | Observed | Sam | 2026-10-24 | Planned |  | 0
D-05 | Closure unsupported | Observed | Jo | 2026-10-23 | Verified closed | 100 | 100
D-06 | Future inspection | Expert review | Sam | 2026-10-30 | Planned | 100 | 50
Use one stable ID per issue. Put the actual observation, requirement, inspector and any limitation in the linked evidence record.
Completed means work performed. Verified closed additionally requires an inspection or review record in Evidence / closure.
Variance is actual less estimate; positive means over estimate. Enter zero explicitly; missing costs withhold the total.
Example rows are fictional and excluded from the Repairs sheet. Extend the 20-row range only after updating formulas and validation.
Project / contract |  |  |  |  | Prepared by / date