## Daily log
Extra work daily quantity and cost log
ArtBuild workbook, version 2026.1. Amber inputs are editable; formulas are protected against accidental edits. General information, not legal advice.
Actual quantities only. A quantity acknowledgement does not itself approve scope, price or payment.
Total CAD
Ticket ID | Date | Change ID | Activity / unit | Category | Signed quantity | Unit cost CAD | Direct cost CAD | Instruction status | Evidence / correction | Review flag
Use total worker-hours once, not crew-hours plus each worker again. Record equipment standby separately and label the unit.
Negative quantities are corrections referencing the original ticket in Evidence / correction. Do not overwrite an original signed record.
Costs exclude overhead markup and tax. Transfer actual costs to pricing once; do not add actual and estimated cost for the same work.
Record weather, delays, delivery returns, witness comments and access constraints on the companion PDF or linked daily site record.
Project / contract |  |  |  |  | Prepared by / date

## Fictional examples
Extra work daily quantity and cost log
ArtBuild workbook, version 2026.1. Amber inputs are editable; formulas are protected against accidental edits. General information, not legal advice.
Actual quantities only. A quantity acknowledgement does not itself approve scope, price or payment.
Total CAD
Ticket ID | Date | Change ID | Activity / unit | Category | Signed quantity | Unit cost CAD | Direct cost CAD | Instruction status | Evidence / correction | Review flag
T-01 | 2026-10-23 | CO-01 | worker-hours | Labour | 6 | 80 |  | Requested | Fictional ticket and site record
T-02 | 2026-10-23 | CO-01 | returned units | Materials | -2 | 25 |  | Requested | Return against fictional ticket T-original
T-03 | 2026-10-23 | CO-02 | standby hours | Equipment | 0 | 50 |  | Requested | Fictional ticket and site record
T-04 | 2026-10-23 | CO-02 | missing rate | Labour | 4 |  |  | Requested | Fictional ticket and site record
T-05 | 2026-10-23 | CO-03 | package | Subcontract | 1 | 500 |  | Requested | Fictional ticket and site record
T-06 | 2026-10-23 | CO-01 | units | Materials | 2 | 25 |  | Requested | Fictional ticket and site record
Use total worker-hours once, not crew-hours plus each worker again. Record equipment standby separately and label the unit.
Negative quantities are corrections referencing the original ticket in Evidence / correction. Do not overwrite an original signed record.
Costs exclude overhead markup and tax. Transfer actual costs to pricing once; do not add actual and estimated cost for the same work.
Record weather, delays, delivery returns, witness comments and access constraints on the companion PDF or linked daily site record.
Project / contract |  |  |  |  | Prepared by / date