## Live records
Deposit dispute materials and commitments
ArtBuild workbook, version 2026.1. Amber inputs are editable; formulas are protected against accidental edits. General information, not legal advice.
Track uninstalled materials and remaining commitments; exclude costs already included in completed work.
Recorded net CAD |  |  | Includes all statuses |  |  | Review before inclusion
Item ID | Scope / item / unit | Counterparty / location | Committed quantity | Unit cost CAD | Gross commitment | Confirmed recovery | Net record CAD | Order status | Evidence / basis | Review flag
Gross quantity times unit cost less confirmed recovery or release gives net exposure. This does not establish recoverability.
Record PO or trade reference, order date, delivery or cancellation action, ownership, due date and responsible person in Evidence / basis.
Use one stable ID per item. Enter zero explicitly. Missing quantities or evidence block the total; duplicate IDs are flagged.
All examples are fictional. Amounts use one consistent tax basis stated in evidence; no tax rate or legal charge is assumed.
Project / snapshot |  |  |  |  | Prepared / reviewed by

## Fictional examples
Deposit dispute materials and commitments
ArtBuild workbook, version 2026.1. Amber inputs are editable; formulas are protected against accidental edits. General information, not legal advice.
Track uninstalled materials and remaining commitments; exclude costs already included in completed work.
Recorded net CAD |  |  | Includes all statuses |  |  | Review before inclusion
Item ID | Scope / item / unit | Counterparty / location | Committed quantity | Unit cost CAD | Gross commitment | Confirmed recovery | Net record CAD | Order status | Evidence / basis | Review flag
EX-01 | Uninstalled doors / each | Fictional Maple Supply | 4 | 100 |  | 0 |  | Ordered | PO01: held on site; return review
EX-02 | Tile cartons / each | Fictional North Tile | 3 | 200 |  | 100 |  | Delivered | PO02: confirmed return credit CAD100
EX-03 | Cancelled trim order / each | Fictional Maple Supply | 0 | 50 |  | 0 |  | Ordered | PO03: no supplied quantity
EX-04 | Special flashing / length | Fictional Roof Supply |  | 80 |  | 0 |  | Ordered | PO04: count and return terms pending
EX-05 | Order quantity correction / each | Fictional Maple Supply | -1 | 100 |  | 0 |  | Ordered | PO05: correct prior recorded quantity
Gross quantity times unit cost less confirmed recovery or release gives net exposure. This does not establish recoverability.
Record PO or trade reference, order date, delivery or cancellation action, ownership, due date and responsible person in Evidence / basis.
Use one stable ID per item. Enter zero explicitly. Missing quantities or evidence block the total; duplicate IDs are flagged.
All examples are fictional. Amounts use one consistent tax basis stated in evidence; no tax rate or legal charge is assumed.
Project / snapshot |  |  |  |  | Prepared / reviewed by