## Scope
Original and revised scope comparison
ArtBuild workbook, version 2026.1. Amber inputs are editable; formulas are protected against accidental edits. General information, not legal advice.
Net value is only revised less original quantity at one comparison rate. It is not an approved change price.
Total CAD
Item ID | Original reference | Revised reference | Unit | Original quantity | Revised quantity | Net quantity | Unit rate CAD | Net value CAD | Approval status | Review flag
Use the same unit and comparison rate for original and revised quantities. For rate changes, use separate documented pricing analysis.
A negative net quantity is an omission. Enter only the net quantity once in the pricing calculator; do not add both original and revised totals.
READY means arithmetic inputs complete, not approved scope or entitlement. Keep approved revision evidence with the change order.
Fictional examples show additions, omissions, zero change and missing data. Actual completed quantities belong in the daily log.
Project / contract |  |  |  |  | Prepared by / date

## Fictional examples
Original and revised scope comparison
ArtBuild workbook, version 2026.1. Amber inputs are editable; formulas are protected against accidental edits. General information, not legal advice.
Net value is only revised less original quantity at one comparison rate. It is not an approved change price.
Total CAD
Item ID | Original reference | Revised reference | Unit | Original quantity | Revised quantity | Net quantity | Unit rate CAD | Net value CAD | Approval status | Review flag
S-01 | Drawing A rev1 | Drawing A rev2 | m2 | 10 | 15 |  | 100 |  | Requested
S-02 | Finish schedule 1 | Finish schedule 2 | units | 5 | 3 |  | 50 |  | Approved
S-03 | Detail 1 | Detail 1 | hours | 0 | 0 |  | 0 |  | Estimated
S-04 | Plan B1 | Plan B2 | m | 10 |  |  | 20 |  | Requested
S-05 | Door list 1 | Door list 2 | units | 4 | 5 |  | 200 |  | Disputed
Use the same unit and comparison rate for original and revised quantities. For rate changes, use separate documented pricing analysis.
A negative net quantity is an omission. Enter only the net quantity once in the pricing calculator; do not add both original and revised totals.
READY means arithmetic inputs complete, not approved scope or entitlement. Keep approved revision evidence with the change order.
Fictional examples show additions, omissions, zero change and missing data. Actual completed quantities belong in the daily log.
Project / contract |  |  |  |  | Prepared by / date