## Evidence
Photo and evidence register
ArtBuild workbook, version 2026.1. Amber inputs are editable; formulas are protected against accidental edits. General information, not legal advice.
Keep originals unchanged. Describe what the image shows; cause and responsibility require separate assessment.
Ready records |  |  | Records to check
Evidence ID | Issue ID | Captured date | Captured by | Location / direction | Original file path | Original or copy | Parent original ID | Access class | Review flag
Capture overall context then detail with scale where safe. Record exact location, direction, date and photographer in the original record.
Use Evidence ID to link inspection notes, measurements, emails and samples. For a copy, enter the original ID in Parent original ID.
This register checks index consistency, not file existence or authenticity. Verify paths and retain metadata and transfer history separately.
Keep client faces, unrelated possessions and sensitive details out of sharing copies where appropriate. Fictional paths are examples only.
Project / contract |  |  |  |  | Prepared by / date

## Fictional examples
Photo and evidence register
ArtBuild workbook, version 2026.1. Amber inputs are editable; formulas are protected against accidental edits. General information, not legal advice.
Keep originals unchanged. Describe what the image shows; cause and responsibility require separate assessment.
Ready records |  |  | Records to check
Evidence ID | Issue ID | Captured date | Captured by | Location / direction | Original file path | Original or copy | Parent original ID | Access class | Review flag
P-01 | D-01 | 2026-10-23 | Sam | North window overall | fictional/P01.jpg | Original |  | Internal
P-02 | D-01 | 2026-10-23 | Sam | North window detail | fictional/P02.jpg | Original |  | Adviser only
P-03 | D-01 | 2026-10-23 | Sam | Annotated detail | fictional/P03.jpg | Annotated copy | P-02 | Approved sharing
P-04 | D-02 | 2026-10-23 | Jo | Trim joint | fictional/P04.jpg | Annotated copy | ABSENT | Internal
P-05 | D-02 |  | Jo | Trim joint | fictional/P05.jpg | Original |  | Internal
P-06 | D-03 | 2026-10-23 | Jo | Repair after test | fictional/P06.jpg | Original |  | Internal
P-06 |  |  |  |  | fictional/duplicate.jpg
Capture overall context then detail with scale where safe. Record exact location, direction, date and photographer in the original record.
Use Evidence ID to link inspection notes, measurements, emails and samples. For a copy, enter the original ID in Parent original ID.
This register checks index consistency, not file existence or authenticity. Verify paths and retain metadata and transfer history separately.
Keep client faces, unrelated possessions and sensitive details out of sharing copies where appropriate. Fictional paths are examples only.
Project / contract |  |  |  |  | Prepared by / date