## Live records
Remaining subcontractor commitments
ArtBuild workbook, version 2026.1. Amber inputs are editable; formulas are protected against accidental edits. General information, not legal advice.
Record remaining exposure after completed trade work is valued elsewhere. Commitments are not automatically client liabilities.
Recorded net CAD |  |  | Includes all statuses |  |  | Review before inclusion
Item ID | Scope / item / unit | Counterparty / location | Remaining units | Cost per unit CAD | Gross exposure | Released amount | Net record CAD | Trade status | Evidence / basis | Review flag
Gross quantity times unit cost less confirmed recovery or release gives net exposure. This does not establish recoverability.
Record PO or trade reference, order date, delivery or cancellation action, ownership, due date and responsible person in Evidence / basis.
Use one stable ID per item. Enter zero explicitly. Missing quantities or evidence block the total; duplicate IDs are flagged.
All examples are fictional. Amounts use one consistent tax basis stated in evidence; no tax rate or legal charge is assumed.
Project / snapshot |  |  |  |  | Prepared / reviewed by

## Fictional examples
Remaining subcontractor commitments
ArtBuild workbook, version 2026.1. Amber inputs are editable; formulas are protected against accidental edits. General information, not legal advice.
Record remaining exposure after completed trade work is valued elsewhere. Commitments are not automatically client liabilities.
Recorded net CAD |  |  | Includes all statuses |  |  | Review before inclusion
Item ID | Scope / item / unit | Counterparty / location | Remaining units | Cost per unit CAD | Gross exposure | Released amount | Net record CAD | Trade status | Evidence / basis | Review flag
EX-01 | Demobilization / crew hour | Fictional Elm Electric | 4 | 100 |  | 0 |  | Requested | T01: remaining work excluded elsewhere
EX-02 | Reserved lift / day | Fictional Crane Trade | 3 | 200 |  | 100 |  | Confirmed | T02: CAD100 release confirmed
EX-03 | Cancelled inspection / visit | Fictional Elm Electric | 0 | 50 |  | 0 |  | Requested | T03: no charge confirmed
EX-04 | Standby / crew hour | Fictional Mason Trade |  | 80 |  | 0 |  | Requested | T04: hours awaiting confirmation
EX-05 | Commitment correction / hour | Fictional Elm Electric | -1 | 100 |  | 0 |  | Requested | T05: reduce prior commitment one hour
Gross quantity times unit cost less confirmed recovery or release gives net exposure. This does not establish recoverability.
Record PO or trade reference, order date, delivery or cancellation action, ownership, due date and responsible person in Evidence / basis.
Use one stable ID per item. Enter zero explicitly. Missing quantities or evidence block the total; duplicate IDs are flagged.
All examples are fictional. Amounts use one consistent tax basis stated in evidence; no tax rate or legal charge is assumed.
Project / snapshot |  |  |  |  | Prepared / reviewed by