## Costs
Suspension cost and mitigation ledger
ArtBuild workbook, version 2026.1. Amber inputs are editable; formulas are protected against accidental edits. General information, not legal advice.
Record actual or estimated costs explicitly. A recorded cost is not automatically recoverable from another party.
Actual net CAD |  |  | Estimated net CAD |  |  | Disputed net CAD
Cost ID | Date | Category | Resource / unit | Signed quantity | Unit cost CAD | Gross cost CAD | Credit CAD | Net cost CAD | Cost status | Source / allocation | Review flag
Never add an estimate and its replacement actual. Reclassify the same current cost ID and retain earlier versions outside active totals.
Credits reduce gross cost once. Negative quantity corrects an earlier charge; link its original record. Do not also enter the same credit.
Use consistent tax treatment and units. Record tax basis, mitigation, avoided costs and allocation in the linked source record.
Summaries separate actual, estimated and disputed amounts. They do not decide causation, entitlement or damages.
Project / contract |  |  |  |  | Prepared by / date

## Fictional cost examples
Suspension cost and mitigation ledger
ArtBuild workbook, version 2026.1. Amber inputs are editable; formulas are protected against accidental edits. General information, not legal advice.
Record actual or estimated costs explicitly. A recorded cost is not automatically recoverable from another party.
Actual net CAD |  |  | Estimated net CAD |  |  | Disputed net CAD
Cost ID | Date | Category | Resource / unit | Signed quantity | Unit cost CAD | Gross cost CAD | Credit CAD | Net cost CAD | Cost status | Source / allocation | Review flag
SC-01 | 2026-10-23 | Demobilization | truck-hours | 4 | 100 |  | 0 |  | Actual | Fictional ticket; ex tax; no legal entitlement
SC-02 | 2026-10-23 | Standby | equipment-days | 3 | 200 |  | 100 |  | Estimate | Fictional ticket; ex tax; no legal entitlement
SC-03 | 2026-10-23 | Site protection | inspection visits | 0 | 50 |  | 0 |  | Actual | Fictional ticket; ex tax; no legal entitlement
SC-04 | 2026-10-23 | Remobilization | crew-hours |  | 80 |  | 0 |  | Estimate | Fictional ticket; ex tax; no legal entitlement
SC-05 | 2026-10-23 | Other | corrected hour | -1 | 100 |  | 0 |  | Actual | Correction to fictional earlier charge
SC-06 | 2026-10-23 | Standby | disputed day | 1 | 200 |  | 0 |  | Disputed | Fictional ticket; ex tax; no legal entitlement
Never add an estimate and its replacement actual. Reclassify the same current cost ID and retain earlier versions outside active totals.
Credits reduce gross cost once. Negative quantity corrects an earlier charge; link its original record. Do not also enter the same credit.
Use consistent tax treatment and units. Record tax basis, mitigation, avoided costs and allocation in the linked source record.
Summaries separate actual, estimated and disputed amounts. They do not decide causation, entitlement or damages.
Project / contract |  |  |  |  | Prepared by / date

## Activity delays
Suspension activity and delay record
ArtBuild workbook, version 2026.1. Amber inputs are editable; formulas are protected against accidental edits. General information, not legal advice.
Calendar spans include both dates. Do not sum overlapping activity durations or infer a project extension.
Recorded events |  |  | Review flags
Event ID | Affected activity | Start date | End date | Calendar days | Overlap group | Owner | Impact status | Evidence / mitigation | Review flag
One row per activity event. Record start and end dates from evidence; missing end dates remain unresolved, not assumed today.
Use Overlap group to identify concurrent events. No summed delay total is provided because concurrency and critical-path effects need review.
Link baseline and revised programmes, access restrictions and mitigation. Reported duration is not an agreed extension or damages amount.
The cost ledger and activity log are separate records. Do not multiply calendar spans into cost claims without an evidenced pricing basis.
Project / contract |  |  |  |  | Prepared by / date

## Fictional delay examples
Suspension activity and delay record
ArtBuild workbook, version 2026.1. Amber inputs are editable; formulas are protected against accidental edits. General information, not legal advice.
Calendar spans include both dates. Do not sum overlapping activity durations or infer a project extension.
Recorded events |  |  | Review flags
Event ID | Affected activity | Start date | End date | Calendar days | Overlap group | Owner | Impact status | Evidence / mitigation | Review flag
SD-01 | Install cladding | 2026-10-23 | 2026-10-25 |  | Overlap A | Fictional planner | Under review | Fictional programme; mitigation pending
SD-02 | Roof delivery | 2026-10-24 | 2026-10-26 |  | Overlap A | Fictional planner | Under review | Fictional programme; mitigation pending
SD-03 | Same-day inspection | 2026-10-23 | 2026-10-23 |  |  | Fictional planner | Under review | Fictional programme; mitigation pending
SD-04 | Open-ended access issue | 2026-10-23 |  |  |  | Fictional planner | Under review | Fictional programme; mitigation pending
SD-05 | Reversed dates | 2026-10-24 | 2026-10-23 |  |  | Fictional planner | Under review | Fictional programme; mitigation pending
SD-06 | Year boundary | 2026-12-31 | 2027-01-01 |  |  | Fictional planner | Under review | Fictional programme; mitigation pending
One row per activity event. Record start and end dates from evidence; missing end dates remain unresolved, not assumed today.
Use Overlap group to identify concurrent events. No summed delay total is provided because concurrency and critical-path effects need review.
Link baseline and revised programmes, access restrictions and mitigation. Reported duration is not an agreed extension or damages amount.
The cost ledger and activity log are separate records. Do not multiply calendar spans into cost claims without an evidenced pricing basis.
Project / contract |  |  |  |  | Prepared by / date